## product backlog
Online Hotel Booking
product backlog Id | priority | user story Id | user story name | Scrum Team Assigned | Risk | complexity | type | completeness creteria | comments
1 | high | user1 | register user | uday | high | high | functional | 10 hrs
2 | high | user2 | login user | uday | high | high | functional | 24hrs
3 | high | user3 | user dashboard | uday | high | high | functional | 30hrs
4 | low | user4 | hotel list | uday | high | high | functional | 80hrs
5 | high | user5 | payment gate way | uday | high | high | functional | 110hrs
6 | low | user6 | booking details | uday | high | high | functional | 40hrs
7 | high | user7 | cancel booking | uday | high | high | functional | 45hrs

## sprint backog 1
ProductBacklog id | UserStoryID | User story num | Task Description | Assigned To | Assigned Date | Estimate time | Status | Actual Time
1 | user1 | 1 | create a necessary class for user and add the reuquired fields | uday | 2024-02-20 | 10 hrs | completed | 8 hr
|  | 2 | take the input from user, and store in database, if no user exists, else throw user already execption |  | 2024-02-20
| user2 | 1 | enter the valid user name password | mahendra | 2024-02-20 | 24hrs | completed | 20hrs
|  | 2 | check username and password from database, if it is valid user is logged in | mahendra | 2024-02-20
|  | 3 | if user idel for 10 mts then logout automatically | mahendra | 2024-02-21
|  | 4 | if user enters wrong username or password, throw some exception message | mahendra | 2024-02-21
3 | user4 | 1 | logged user can able view all the hotels with in range of 3km | ratnam | 2024-02-22 | 80hrs | completed | 65hrs
|  | 2 | we can filter hotels by pricing,distance,rating,eminities,etc., | ratnam | 2024-02-23
|  | 3 | updating the hotel list based on filters | ratnam | 2024-02-24
|  | 4 | hotels details are shown to the user selected | charan | 2024-02-25
|  | 5 | availability of rooms for the selected date and time,and number of persons is shown to the user | charan | 2024-02-26
|  | 6 | if there are are no availability of rooms a popup is shown "NO AVAILABILITY OF ROOMS" | charan | 2024-02-27
|  | 7 | if a room is selected by the user he is redirected to the payment gateway | charan | 2024-02-28
4